## By Project
Marketing Task Tracking
Instructions: Tracking tasks and activities for your marketing can be done in a variety of formats. This Excel® tool provides a few simple options to help you track the detailed tasks and activities for each item on your marketing calendar. We recommend using a project management technology to track your projects, tasks and due dates. However, as a best practice, use whatever method will help hold you accountable to your commitments. |  |  |  | © 2021 Educe, Inc.
MARKETING TASKS: BY PROJECT
EXAMPLE MKT PROJECT: COI MARKETING SET UP
Task | Assigned To | Due Date | Notes
ESTABLISH ANNUAL TIMELINE & DUE DATES FOR ALL TASKS | PRACTICE MGR | 2020-10-15 | Sets up COI Marketing Plan, establishes projects and sets timelines.
SET COI TIME IN ADVISER ANNUAL & WEEKLY CALENDAR | ADMIN | 2020-11-01 | Included in October annual calendar update process
GATHER CURRENT CLIENT COIs | ADMIN | 2020-11-15 | Ideal clients are priority
ESTABLISH LIST OF POTENTIAL COIs | ADVISER | 2020-11-15 | Research local groups with similar idea, google local area, infousa.
DRAFT COI INTRO SCRIPTS/ QUESTIONS | ADVISER | 2020-12-16 | Set during marketing plan time
REVIEW LIST OF CURRENT COIs | ADVISER | 2020-12-16 | Set as 2x month recurring in mkt plan time
BUILD COI REFERRAL ROADMAP PROCESS INTO PROSPECT PROCESS | PRACTICE MGR | 2020-12-30 | Set task timeline for each process step
BUILD COI PROFILE PROCESS | PRACTICE MGR | 2020-11-30 | Set task timeline for each process step
BUILD ”TAX TIME TREATS” PROCESS | PRACTICE MGR | 2020-01-15 | Set task timeline for each process step
BUILD COI TOUCH POINT & COMMUNICATION CALENDAR | PRACTICE MGR | 2020-11-15 | Set task timeline for each process step
BUILD CLIENT ADVISORY TEAM PROCESS | PRACTICE MGR | 2020-11-30 | Set task timeline for each process step
ADMIN SCHEDULES WEEKLY LUNCHES | ADMIN | 2020-11-15 | Set as a recurring item on task list
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
MKT PROJECT: INSERT HERE
Task | Assigned To | Due Date | Notes
© Educe Inc. ¦ Limitless Advisor Limitless materials may not be reproduced, used, or sold in whole or in part, in any manner, without written consent or license for use by Educe, Inc. en consent or license for use by Educe, Inc.

## By Month Template
Marketing Task Tracking
Instructions: Tracking tasks and activities for your marketing can be done in a variety of formats. This Excel® tool provides a few simple options to help you track the detailed tasks and activities for each item on your marketing calendar. We recommend using a project management technology to track your projects, tasks and due dates. However, as a best practice use whatever method will help hold you accountable to your commitments.
© 2021 Educe, Inc.
MARKETING TASKS BY MONTH TEMPLATE
JANUARY
Task | Marketing Project | Assigned To | Due Date | Notes
FEBRUARY
Task | Marketing Project | Assigned To | Due Date | Notes
MARCH
Task | Marketing Project | Assigned To | Due Date | Notes
APRIL
Task | Marketing Project | Assigned To | Due Date | Notes
MAY
Task | Marketing Project | Assigned To | Due Date | Notes
JUNE
Task | Marketing Project | Assigned To | Due Date | Notes
JULY
Task | Marketing Project | Assigned To | Due Date | Notes
AUGUST
Task | Marketing Project | Assigned To | Due Date | Notes
SEPTEMBER
Task | Marketing Project | Assigned To | Due Date | Notes
OCTOBER
Task | Marketing Project | Assigned To | Due Date | Notes
NOV
Task | Marketing Project | Assigned To | Due Date | Notes
DECEMBER
Task | Marketing Project | Assigned To | Due Date | Notes